AIM          PRIMARY DRIVERS              SECONDARY DRIVERS                  CHANGE CONCEPTS

Theatre etiquette/practice

Optimise- Traffic, cleaning, Hand Hygiene, Bare below Elbow, PPE donning and removal, skin prep technique

Theatre etiquette -Sept Update

Theatre audit performed April 18, practice issues reflect all members of the MDT Follow up audit complete with some improvement, repeat audit planned.

Optimise the

care of Cardiac wounds

September 18

Update

Surgical Skin Prep -Sept Update

Chloraprep agreed by SSCGG 15/06/18 to be made available for use

No consensus on use of Chloraprep.

Education session on surgical prep  delivered by cardiac surgical staff.

Sites for hair clipping poster in development with Comms.

Surgical Skin prep

Consider Chlorhexidine 2%/Agree method

Consistent and clear process for-

- Routine cardiac wound dressing & duration of application

- Defined points for wound assessment

- Minimum dataset for wound documentation

Impact of Mediastinal drains/Pacing wires removal on day 1 or 2 on dressing integrity

Surgical dressing & Wound review/documentation - Sept Update

- New regime agreed in principle, however not implemented due to further disagreement by surgeons. Escalated to JB and LG.

- Points for dressing change and wound documentation agreed- await dressing choice to be resolved before progressing.

- Intent to ensure space between sternal and drain dressings to minimize dressing disruption

- Compliance auditing planned  when dressing product agreed

- Wound photography to aid to wound review within MDT. Challenges noted with expired wound photography policy, location of storage of image and staff to take pictures. Testing planned late September.

Duration of application of surgical dressings

Defined points for wound assessment and documentation

Mechanical breakdown in females

Adequate breast support post op

Mechanical Breakdown in Females- Sept Update

BHIS bra still under consideration- In meantime the cardiac booklet and face to face education give clear reminders re need for breast support

Cardiac Booklet- updated and with printers, although SSI prevention content limited and expectations re scar not included.

Pre op video on reducing SSI- filming planned October. Wound expectations included in the video

Appropriate indication for wound sample

Wound swab competency review and poster developed- Complete CLOSED

Accurate SSI diagnosis

Wound review prior to prescribing antibiotics

ANP/Ward Prescribing- Sept Update

- ANP team confirm anti B prescribed on basis of micro & clinical features

- Antibiotic therapy is reviewed on transfer from HDU.

- Resources provided to ANP team re SSI definitions

- Antibiotic initiation for SSI where SSI definitions are not met should be recorded as surgeon request within patient’s notes.

- ANP are taking active role in viewing cardiac wounds where issues are noted.

Clear process for OPD wound review and post discharge referrals back to GJNH

Clear process for medical review where required at TV clinic

Clear process for discharged patients/Primary care to refer back to GJNH

New wound discharge form developed. CLOSED

Standardised wound info to primary care

Complex Wound photography on discharge –Sept Update

Cardiac rehab have stated in addition to the issues highlighted above, their capacity to take forward photography on discharge. This will be discussed further with CNM.

Consistent Discharge Information

Clinic referral & medical input process to clinic COMPLETE/CLOSED

Accurate/full data collection for HPS

SSI Data Collection- Sept Update

SSI Surveillance Meetings ongoing to improve data completeness with Theatres, CC and Ward ongoing