Ref: GJF/2017/02/10

# Board Meeting:		16 February 2017

Subject: 	Business Services Patient Activity Performance Report - December 2016

Recommendation:	Board members are asked to note the report.

__________________________________________________________________

## 1	Background

Patient activity is reported on a monthly basis, both by month and year to date.  Data is primarily measured in episodes of care.  However, data is also captured to reflect the number of procedures being carried out by Board, by specialty.  This information is particularly relevant to referring Boards who are allocated activity and measure their activity/throughput at the Golden Jubilee National Hospital in numbers of procedures.

Appendix A to this document is provided for information purposes and reflects the number of patients treated against an annual plan of 14,946 (patients).

Appendix B to this document is adjusted to represent theatre slots used (as opposed to numbers of patients) in both orthopaedic surgery and plastic surgery.  This allows us to more accurately reflect actual theatre utilisation and allows us to focus on maximising the theatre capacity that is available to us.

Referring Boards receive a monthly monitoring document which provides them with a detailed breakdown of the number of patients referred, their complexity and the number of theatre slots used to treat them.

- Operational Governance

Inpatient/Day Case/Diagnostic Imaging Activity Analysis December 2016

Activity for inpatients/day case procedures measured against a projection of 14,946 (which excludes cardiothoracic/cardiology activity) was behind plan by 6.2% for the month of December and ahead of the year to date plan by 0.4% when activity is adjusted to reflect complexity (Appendix B).

Measured against a total activity projection of 37,871, the combined inpatient/day case and imaging activity at the end of December was 8.0% ahead of plan year to date when adjusted to reflect complexity (Appendix B).

3	Analysis of Performance Against Plan at End December 2016

3.1	Orthopaedic Surgery

The annual target for orthopaedic joint replacements for 2016/17 is based on 3,700 primary joint replacements. This number is calculated on the basis of one patient to one theatre slot. Each session equals two primary joint theatre slots.  However, based on experience over the recent years, we have made the assumption that the number of complex joint replacements likely to be referred for treatment would be approximately 9%. These procedures typically take the equivalent theatre space of 1.5 - 2 primary joint replacements.

In addition to the 3,700 primary joint replacements, there is a target of 1,020 orthopaedic non joint procedures and 456 foot and ankle procedures for the year. This equates to a total of 5,176 orthopaedic theatre slots per annum (as documented in Appendix B).

At the end of December, orthopaedic joint activity was ahead of the year to date plan by 149 primary joint replacements and 221 foot and ankle procedures.  However, orthopaedic ‘other’ activity was behind plan by 251 procedures.  Throughout 2016, there has been a higher than expected demand for foot and ankle surgery which will be offset against the lower than expected ‘orthopaedic other’ activity.  On the whole, orthopaedic surgery is currently exceeding the year to date plan.

3.2	Ophthalmic Surgery

Ophthalmology activity remains very high behind plan for the month by 45 procedures and 69 procedures year to date.

3.3	General Surgery

General surgery has again performed ahead of plan by 30 procedures in the month of December and is 180 procedures ahead of plan year to date.  Weekend operating lists continued in December to support referring Boards.

3.4	Plastic Surgery

For reporting purposes Plastic Surgery has been split and will be monitored throughout 2016/17 as hand surgery, minor plastic surgery, and major plastic surgery.

The delivery of hand surgery activity in the month exceeded our plan for December by nine procedures and is currently 118 procedures ahead of plan year to date.

The lack of Plastic Surgeon availability continues to present a significant challenge and, consequently, minor plastic surgery remains behind plan by 92 procedures and major plastic surgery is behind plan by 179 procedures year to date.  Recovery of this situation is under constant review, however, a solution to this is unlikely to be imminent.

3.5	Endoscopy

The endoscopy service performed slightly behind plan by 13 procedures in the month of December and is behind the year to date plan by 35 procedures.  It is our expectation that this shortfall will be recovered as we progress through the year.

3.6	Diagnostic Imaging

In order to meet the demands of referring Boards, agreement has been reached for the mobile Magnetic Resonance Imaging scanner to remain on site at GJNH for the full year.  The activity associated with the mobile unit is included in full year target number.  Activity has remained high and for the month of December, Diagnostic Imaging significantly exceeded the plan by 269 examinations and is currently ahead of the year to date plan by 2,243 examinations (13%).

4	Current Situation

- Weekend general surgery lists will continue until the end of the financial year.

- Delivery of the Plastic Surgery service remains an ongoing challenge due to the availability of Plastic Surgeons. Discussions are currently under way with the referring Board around the sustainability of this service.

- Ophthalmology activity was predicated on the recruitment of additional ophthalmic surgeons.  Two surgeons were recruited in quarter three; one was expected to take up post in January 2017 and the other is not expected to take up post until May 2017. There has been a delay in the arrival of the Ophthalmic Surgeon we expected to arrive in January; this is currently presenting operational challenges and is likely to continue to result in a shortfall in ophthalmology.

- Plans have been progressed to commission a mobile ophthalmology unit on the GJF site. The intention is to:

  - commission a mobile theatre for three days per week commencing end March/April 2017;

  - provide capacity for approximately 2,800 additional outpatients resulting in approximately 2,100 additional cataracts in a full year;

  - move the current ophthalmology outpatient clinic to level four to accommodate the additional patients who will need to be seen to populate the additional theatre lists;

  - commission visiting consultants as necessary to support this activity; and

  - recruit additional staff to deliver the additional activity.

- The Recovery Group will continue to meet on a weekly basis to scrutinise theatre utilisation and address any shortfalls in activity as they arise.

June Rogers

Director of Operations

31 January 2017